## Sheet1
Reported Date | Reported By | Severity | Status | Assigned To | Bug Description | Expected Results | Actual Results | Steps to Reproduce | Suspected Systems + Solution Ideas | Media (if needed to show bug).
2025-02-22 | Dieter | P3 (annoying, loss of marks) | In-progress | Dieter + Matias | Really fast moving platforms can sometimes 'wander off'. | The platforms should never leave the defined path. | When moving REALLY fast, it is possible for the platform to shoot off into the distance, missing the end stop. | 1. set moving platform speed really high. 2. activate accelerate. Will not happen every time, and is pretty rare. | Physics system. The platform is likely overshooting the end of it's stage in the movement path. This causes it to never pass the check for transitioning to the next movement path. Solution -> need a better check that will trigger if the platform goes past the end stop in the direction of movement. This is more prominent with game lag
2025-02-23 | Dieter | P5 (nice to have) | Resolved |  | Player hitbox is too wide | The player should not be able to 'hang' off an edge. | The player can walk past the edge as their hitbox width is determined by the head not feet. | 1. walk really close to an edge. | Just need a small convex mesh for the player that is smaller around the feet.
2025-03-05 | Dieter | P0 (crash) | Resolved | Dieter | RACE CONDITION: during reset or level load, there is a possible race condition. If you hit the move buttons exactly when the world is resetting, it is possible to trigger the assert in the .get for the motion inside of player motion. This is because the level is not set up yet, but the async input handler calls functions... | Game does not crash, player does not move during reset | Game crashes | Hard to reproduce. Only found because of a bug in physics that infinitely triggered the game reset | Transition the systems manager to a state machine that does not step other systems during reload
2025-03-10 | Dieter | P4 (annoying, but could be left as-is) | Resolved |  | Physics objects are slightly squishy. They can be pushed into each other. If pushed hard enough, they can pass through each other. | The objects are rigid and cannot pass through each other | The objects sligthly overlap before returning to their normal positon a few frames later | 1. find a physics object (bolts, projectiles) 2. push it really hard into a wall or another object | Solution is to perform multiple steps of physics per frame. The optimizaiton to make this possible has been done, but the sub-stepping behaviour has not been implemented for this milestone.
2025-03-10 | Dieter | P3 (annoying, loss of marks) | Resolved |  | Vertical platforms don't reliably fling the player. | Fast moving vertical platforms will fling the player upwards. In a sense, the player will keep the momentum of the vertical platform. | The player simply falls when the platform changes direction. | 1. find a fast moving vertical platform 2. accelerate time | Something to do with physics stepping. It works if we do not use a fixed time step and the game runs at like 900 fps lol.
2025-03-10 | Dieter + Yixian | P3 (annoying, loss of marks) | Resolved | Yixian | When standing on physics objects such as the bolt projectiles, jumping does not always work | The player can jump if they are standing on anything | Sometimes, pressing jump does not trigger a jump | 1. stand on the bolts in L1. 2. try jumping, run around a bit and jump on/off if it does not trigger | Collision normal? Potential solution -> roadrunner effect, Yixian is attempting this
2025-03-10 | Dieter | P3 (annoying, loss of marks) | Won't Fix |  | Spikes trigger death from any angle | The spike only kills the player if the touch the "spikey" part. | If any part of the player collides with a spike, they are killed | In L1, slowly approach the spikes. Observe as you are killed as soon as the player BB touches any part of the spike. | Resolve the collision with the normal plus the direction of the spike component. Also prob an effect of the epsilon added to keep players grounded
2025-03-10 | Dieter | P3 (annoying, loss of marks) | In-progress |  | Cannon towers do not account for gravity when aiming. Tend to shoot in front of the player. | The cannon tower hits the player | The cannon tower shoots slightly in front of the player | Stand in front of cannon tower. Wait for it to shoot. Observe as it shoots in front of you | Aim slightly higher? could aim higher based on distance?
2025-03-10 | Yixian | P3 (annoying, loss of marks) | Open |  | Unexpected height of jumping, potentially at corners | Player jumpinng at arbitrary location should lead to the same result (same height of jumping). | In some cases, the player jumps to an unexpected height (~3 times higher than expected); sometimes it seems the player automatically jumps after colliding/landing on edges | Currently unknown | Potentially collision resolution mechanisms, related to velocity adjustment after PhysicsObjects overlap
2025-03-11 | Dieter | P3 (annoying, loss of marks) | Resolved |  | Changing level while in time controlled -- the new level will not start with the right time control state | The game should reflect the time control state -- either reset or load in correct state | The game leaves the screen shaders on (still in time slowed down state), but none of the time control components are loaded with the right values | Start time control (speed up or slowdown), change level (1 or 2)
2025-03-25 | Kevin | P4 (annoying, but could be left as-is) | Resolved |  | Boss moves diagonally and then snaps back to its intended x position during the rise animation of ground slam attack | The boss should rise directly upwards | Boss rises diagonally and then snaps back to the original x position | Boss has reached phase 2 (at or below 80% total health) | Animation or Boss Systems (either the velocity is not set properly during state transition or the animation rendering is showing how it is sliding over a png)
2025-03-25 | Dieter | P3 (annoying, loss of marks) | Open |  | Rotating obejects can slightly overlap with other objects | Collsion resolution should prevent objects from overlapping | On rotation, objects can slightly rotate into each other | Put a large spikeball on a corner and watch as it slightly rotates into the platform. Observe the gears as they turn | Collsion detection/physics
2025-03-25 | Dieter | P3 (annoying, loss of marks) | Open |  | Dynamic rotation is a bit buggy for fast moving objects (spikeballs and large rotating gear in the main Decel Level) | Rotating objects should turn naturally with their motion. (ie object moving left should rotate CCW). Stable objects should stop rotating. Sometimes objects randomly bounce when they have high angular velocity | Rotation isn't natural all the time, sometimes objects rotate in the wrong direction or spin up infinitely. | Go to the decel level and observe the spike balls moving horizontally or the large spinning gear. | Physics, handle rotational dynamics
2025-03-25 | Dieter | P3 (annoying, loss of marks) | Open |  | Composite meshes are not perfect, specifically gears | Meshes should match the sprite perfectly | There are some minor errors between composite meshes and sprites | Step on the large gear and observe as the player can slightly overlap with the gear sprite. | World init stiching together the decomposed mesh
2025-03-25 | Dieter | P3 (annoying, loss of marks) | Open |  | DECEL LEVEL: large moving gear can get stuck, move the wrong way, or not roll at all. | The gear should roll and not get stuck | The gear can get stuck or spin up forever. | Go to the decel level and observe the large frolling gear | Physics, handle rotational dynamics
2025-03-25 | Kevin | P3 (annoying, loss of marks) | Open |  | Snooze button is sometimes not rendered properly, and incorrectly triggers player snooze button collision after the player has collided it for the first time in the boss fight | The snooze button should be rendered properly. The collision only occurs when the player and the snooze button actually collides. | After the snooze button has been rendered once, there is a chance that it will not properly rendered and collision will be detected despite there not being a collision. | Hit the snooze button for the first time in the boss fight. Survive until future instances when the boss becomes exhausted again. Sometimes, the snooze button is rendered. Sometimes, it is not. | Physics or Boss System,
2025-03-24 | Yixian | P4 (annoying, but could be left as-is) | Open |  | In flying mode, player can be flung away from the game scene when getting in contact of the side of a moving platform | Player stays in the scene regardless of any interactions | As described, player could get flung to very far | Toggle fly mode (M); go towards the side of a horizontally moving platform; can use acceleration mode to see a more obvious result | Due to the decision that player in flying mode subjects to 5 times acceleration and no velocity clamping; currently a developer decision that will not be considered a bug; will not be delivered to actual release.